Northland Community and Technical College

Enrollment Management Plan

Northland Community & Technical College, with campuses in Thief River Falls and East Grand Forks, Minnesota is a public post-secondary institution dedicated to the philosophy of providing liberal arts and technical education with curriculum designed to meet the educational needs of high school, special needs and adult students.

It is the belief of the Enrollment Management Team that a strategic enrollment management plan is the key element to the success and growth of our college.

This enrollment management plan identifies broad goals, with specific objectives, responsible parties and time lines. It is the responsibility of the enrollment management department to develop the action plan required to be successful. This action plan will include, but not be limited to procedures, timelines, goals, evaluations, and recommendations as to changes and modifications.

	


Vision Statement

Northland Community and Technical College will be widely recognized as a student focused, dynamic college with excellent educational opportunities that has strong partnerships with businesses, educational institutions, and communities it serves.

	


Overall Goal

Overall Goal: To build a comprehensive enrollment management plan that will achieve Fall 2007 -2008 enrollment goals.

	


	


Situation Analysis

Declining high school enrollments: Enrollments at schools in our service area have been in a steady decline, since the mid 1980’s. In that time thirteen area high schools in NW Minnesota have consolidated with other school districts due to low enrollment. 

Twenty-five percent of the nation’s public K-12 students attend rural or small – town schools, those in communities of 25,000 people or fewer. Within our immediate service area there are three communities of that size. A report from the Rural Schools and Community Trust (1997-98) states, “Changes are needed in those states because students’ parents are among the poorest and least educated, their teachers are the worst paid and their communities are the least able to support school programs.”

Competition from four-year institutions is on the rise; these schools have become more aggressive in their recruiting of this service area. Many of these colleges offer students scholarships or financial packages that we cannot match. Our Northland College Foundation is active in raising funds, but as a two - year school we have very limited resources that would entice a student to enroll at our school over another. Currently there is no active Foundation Office on our East Grand Forks campus.

In our main recruiting area of Northwestern Minnesota and Northeastern North Dakota there is some fierce competition for area high school graduates. In this region, we must contend with recruiters from the University of Minnesota – Crookston, University of North Dakota, Lake Region College, Bemidji State University, Minnesota State University - Moorhead, Mayville State University, North Dakota State University, North Dakota State College of Science, Concordia College, and Minnesota State Community and Technical College –Fergus Falls Campus, Moorhead Campus, Detroit Lakes Campus, and Wadena Campus and Northwest Technical College – Bemidji. With the exception of the Minnesota State Community and Technical College – Wadena and Fergus Falls Campuses, North Dakota State College of Science, and Lake Region College, all other colleges or universities are within a 125 - mile radius of Thief River Falls or East Grand Forks, creating a large demand for our area graduates.

July 1, 2003, Northland Community and Technical College in Thief River Falls and Northwest Technical College – East Grand Forks merged into one institution, to become Northland Community and Technical College, Thief River Falls and East Grand Forks. This is a unique merger that has allowed our two campuses within sixty miles of one another and with a similar academic mission to be under the umbrella of a consolidated two year comprehensive college. 

The East Grand Forks campus offers a wide range of majors, but is recognized as a center of excellence in allied health-related career opportunities. Students complete programs such as Cardiovascular Technology, Practical Nursing, Para medicine, Clinical Lab Science, Medical Assisting, Surgical Technology, Radiology, and Fire Technology.  Originally founded in 1972, the campus has grown continuously and currently has 1,300 full time students. 

Northland Community and Technical College has a definite bonus as being the only comprehensive college in Northwestern Minnesota. We are able to offer students an alternative to the traditional college scene, where students can get the first two years of most four - year programs in a smaller more family oriented atmosphere. They may enroll in one of our many technical programs that prepare them for immediate entry into the workforce. Currently Northland Community and Technical College offers over 30 majors as well as 50 plus career programs for students to choose from. Our nationally recognized Aviation Maintenance Program headlines the Thief River Falls campus occupational programs; it is complimented by programs in Nursing, Criminal Justice, Mass Communications, Welding, Auto Body, Architecture, Automotive Service, Accounting, Sales Marketing Management and others. 

 As a comprehensive community and technical college, Northland College is able to offer students a wide variety of activities. They may get involved in a new area of interest or pursue an interest that they already have. Students may choose from various clubs and organizations and activities including varsity sports.

	


	


Fall 2007 - 2008 Goals

( Achieve a full-time student enrollment of 2580

Note: These figures reflect a 3% increase over FY 2006 combined fulltime enrollment on both campuses, which includes On-Line students.
( Responsibility: Enrollment Management

(Timeline: Fall Semester 2007
( Achieve a total unduplicated headcount of 5155 students 


Note: This number reflects the total number of students enrolled full and part-time at Northland College including Distance Education, Farm Business Management and Custom Training that the Northland College Enrollment Management team does not recruit for.


( Responsibility: Enrollment Management

( Timeline: Fall Semester 2007
( Achieve an enrollment of 2922 FYE for Fall 2007-2008 
( Responsibility: Enrollment Management

( Timeline: Fall Semester 2007
Note: Reflect a 3% increase over FY 2006
(Achieve a total enrollment of 10% among minority students enrolled at Northland Community and Technical College
● Continue to offer cultural events on campuses and invite the community.

● Continue working with special populations on tours, job shadowing and mentorship programs.

● Current minority student population stands at 8.27 % campus wide, overall goal to increase this to 10% for fall 2007 – 2008.


Note:  Fall semester 2006 our combined minority student population was at 414 students’ campus wide.  

Ethnicity:


Native American 
168
3.0 %
Fall 2006     
119 Fall 2005

African American
133
2.6 %
Fall 2006
106 Fall 2005

Asian


  38
.007 %
Fall 2006           35 Fall 2005 

Hispanic

  72
1.4 %
Fall 2006           65 Fall 2005

Pacific Islander
    3
-
Fall 2006             4 Fall 2005
Total                                        414      8.27 %                         329 6.29%     


( Responsibility: Director of Multicultural Services

( Timeline: Fall Semester 2007
	


Key Recruitment Strategies

( To increase image and awareness of Northland Community and Technical College
Continue to promote and conduct individual campus visits, group visits, tours, special events, demo-days, open house, and athletic events.


( Area high schools.

( Television, radio, print, publications.

( Communities.
( PSEO.
( To generate a sufficient number of inquiries to achieve enrollment goals


Utilize recruiting staff in most efficient way to cover immediate service area.  Promote unique programs at NCTC: aviation maintenance, architectural technology, criminal justice, allied health programs etc. Add, develop or enhance programs that will attract new students to NCTC, Pharmacy Tech, Massage Therapy, and Early Childhood. Through the use of direct mailings, publications, ACT rosters etc, contact those perspective students that may be interested in NCTC. 

( High school visits.
( Career fairs.
( Minority student career fairs. 

● Job fairs.
( Internet/website inquiries.

( ACT results.

( Applications.

( Financial aid applications.

( Direct mailings.

● Telephone inquiries.

● Reciprocity agreements with surrounding states

( Develop a college wide-system for capturing, coding and qualifying inquiries 


Utilize the MnSCU Integrated Student Record System. This system will allow data entry on new student prospects, utilize our mail merge capabilities for pattern day intervals, create major letter paths, and create a communications menu to process letter sequence and process prospect flow.

( Set a department goal of 5-day turn around on all inquiries received.
● Prospect letters will be processed on a weekly basis.

(  Assist in the revision and development of promotional publications to support the recruitment process

( Non-traditional program needs.


●Telephone inquiries. 

●To conduct special events and campus visit programs to maximize number of personal contacts and enrollment rates. 
( Campus visits.
( High school class visits (occupational classes).
( Program days, welding demo, honor band, theater, athletic tournaments, etc. 

( Financial aid services available for minority and underrepresented student populations.
● Host various regional high school board meetings.

( Invite local school boards, administration, faculty and counselors to campus.

● Host Northwest Minnesota Counselor Association meetings on campuses of NCTC annually.
( Develop an effective Student Ambassador program that includes the use of current students 

( Utilize campus ambassadors in the entire recruiting process.

● Tours
● Special Events

● Career Fairs

( Develop enrollment plans for students in targeted segments
( Increase enrollment of minority students overall to 10 percent college wide.

( Enhance current monthly celebrations on campuses; Black History Month, Celebramos, Native Images Month and Women’s History Month.

( Utilize ISRS system to capture, analyze and detail all communications with minority and non-traditional students.

( Develop recruiting guide and calendar for the recruitment of minority, nontraditional and underrepresented students. Complete high school visits, career fairs, minority career fairs, in Minnesota, North Dakota and South Dakota. 
●Development of new brochures, such as, Multicultural Services, Mentorship Program, Perkins Grant, New Ventures Center, and Underrepresented Programs.  

( Enhance current relationship with Perkins grant as to allow NCTC to expand minority, non-traditional and underrepresented student and program recruiting efforts.  Example: Out state career fairs, minority career fairs in metro region of Minneapolis and St. Paul. North and South Dakota high school and college career fairs.

●Visits to tribal and public schools on the White Earth, Red Lake, Leech Lake, Turtle Mountain and Spirit Lake Reservations to include tribal colleges. 

(  Foster on going partnerships with community and other agencies such as; Tribal Colleges, Higher Education Committees, Minnesota Indian Scholarship, MN Association of Counselors of Color, Reservation Talent Search Offices, MN School Counselors Association, and Staff Development and Continued Education.
( The Director of the New Venture Center - TRF & Equity Coordinator - EGF are available to provide presentations to area high school classes about what nontraditional careers and underrepresented programs are and the advantages nontraditional careers provide.








( Offer hands-on exploratory workshops and Career Exploration Days designed specifically for women and men considering nontraditional careers and underrepresented programs.
● Attend, as a campus, the Minnesota State College and University System Underrepresented Student Conference held annually in Twin Cities. Which was last attended by college staff in the spring of 2006. 
(Continue to expand Mentor Program and Job Shadowing that was implemented fall of 1999, aided by the continued development of new materials and brochures. 

(Develop a means of sharing recruitment information with members of the faculty, staff and administration on both campuses of Northland Community and Technical College.

( Employee Updates.

( Pioneer Weekly.

( General Matters Meet and Confer

( Improve the college’s ability to communicate electronically with prospective students
· Respond immediately to all incoming internet requests for information.

· Utilize e-mail addresses given to us by prospective students. 
· Stay in contact with students electronically with NCTC updates.

· Update NCTC WebPages with help and guidance from school Webmaster. 

· Develop a calendar to update Web Pages.

· Calendar of NCTC events posted on NCTC website, www.northlandcollege.edu .

	


Enrollment Management Action Plan

To build a comprehensive enrollment management plan that will achieve Fall 2007 enrollment goals.
	


Key Strategy 1: 
To increase image and awareness of Northland Community & Technical College

Action Plan: 
Through the use of individual campus visits, group visits, special events, Demo-Days, Open House, and athletic events make the public more aware that Northland Community and Technical College is a comprehensive college in Northwestern Minnesota with campuses in East Grand Forks and Thief River Falls.

Responsibility: 
Director of Enrollment Management, Admissions Representatives, Director of Multicultural Services, Admissions Offices, Public Relations Director and Marketing Director.

Time Line: 


On going.

Cost:


Recruiting Budget (Approx. $45,000 annually)

Minnesota High School Visits (125)
	Ada – Borup
	Aitkin
	Albany
	Albrook
	Alexandria

	Aurora
	Babbitt
	Badger
	Bagley
	Barnesville

	Barnum
	Battle Lake
	Baudette
	Bemidji
	Bertha-Hewitt

	Bigfork
	Blackduck
	Brainerd
	Breckenridge
	Browerville

	Cass Lake
	Carlton
	Cherry
	Chisolm
	Clearbrook

	Climax
	Clinton-G-B
	Cloquet
	Cook
	Cromwell

	Crosby-Ironton
	Crookston
	Deer River
	Detroit Lakes
	Duluth Central

	Duluth-Denf’ld
	Duluth-East
	Duluth-Marsh.
	Eagle Valley
	E. Grand Forks

	EGF – S.Heart
	Ely
	Erskine
	Esko
	Eveleth-Gilbert

	Fergus Falls
	FF – Hillcrest
	Fertile
	Fisher
	Floodwood

	Fosston
	Frazee
	Glyndon
	Goodridge
	Grand Rapids

	Greenbush
	Grygla
	Hallock
	Halstad
	Hawley

	Hermantown
	Herman
	Hill City
	Hibbing
	Indus

	Int’l. Falls 
	Karlstad
	Kelliher
	Lake Park
	Laporte

	Lancaster
	Little Falls
	Littlefork
	Long Praire
	Mahnomen

	McGregor
	Melrose
	Menahga
	Mesabi East
	Monticello

	Moorhead
	Moose Lake
	Mountain Iron
	Nahwauk
	Nevis

	NY Mills
	Newfolden
	Northland
	Northome
	s

	Park Rapids
	Pelican Rapids
	Pequot Lakes
	Perham
	Pine River

	Plummer
	Proctor
	Red Lake
	Red Lake Falls
	Roseau

	Rothsay
	Royalton
	Sandstone
	Sartell
	Sauk Centre

	Sauk Rapids
	Sebeka
	Silver Bay
	Staples-Motley
	Stephen

	St. Cloud 
	St. Cloud Cath.
	St. Cloud Tech
	St. Michael
	T.R. Falls

	Warroad
	Warren
	Waubun
	West Central
	Wheaton

	White Earth
	Willow River
	Wrenshall
	
	


North Dakota High School Visits (65)
	Adams
	Ashley
	Bellcourt
	Bisbee
	Bottineau

	Cando
	Casselton
	Carrington
	Cavalier
	Central Valley

	Devils Lake
	Drake
	Drayton
	Dunseith
	Edgely

	Edinburg
	Ellendale
	Fargo Oak Gr
	Fargo North
	Fargo Shanley

	Fargo South
	Fessenden
	Finley-Sharon
	Fordville
	Grafton

	GF Central
	GF Red River
	Griggs Cnty.
	Hatton
	Harvey

	Hillsboro
	Hope-Page
	Jamestown
	Lakota
	Langdon

	Larimore
	Leeds
	Maple Valley
	Mayville
	Midkota

	Midway
	Minnewauken
	Minto
	Munich
	New Rockford

	Northwood
	Park River 
	Pembina
	Petersburg
	Rock Lake

	Rolla
	Rollette
	Rugby
	Sheyenne
	St. John

	St. Thomas
	Starkweather
	Thompson
	Valley City
	Wahpeton

	Walhalla
	Warwick
	West Fargo
	Four Winds
	Northern Cass


Demo Days

	Career Exploration Days TRF (2) EGF (1) 
	Mentor Program
	Aviation Open House


	


Key Strategy 2:


To generate a sufficient number of inquiries to achieve enrollment goals
Action Plan: 
Utilize enrollment management team in most efficient way to cover service and recruitment area. Current expanded recruitment territory includes Northern Minnesota (Brainerd to Baudette), the Arrowhead region of Minnesota, the Eastern 1/3 of North Dakota, and a limited number if career fairs in South Dakota. Recruitment territories also include, but are not limited to, Minnesota Education Fairs, Dakota Counselors Association Career fairs, South Dakota Counselors Association Career fairs, as well as the National College Fairs in Minneapolis, Milwaukee and Chicago.
Enrollment Management Team
Director of Enrollment Management – Supervises Enrollment Management staff.

Director of Multicultural Services – Duties include recruiting at area high schools, minority career and job fairs, Eastern South Dakota Career Fairs and Minnesota Association of Counselors of Color career fairs throughout Minneapolis/St. Paul.

Advisor/Recruiter (TRF) – Duties include recruiting at area high schools, career fairs, and national college fairs.  Conducts campus tours as needed.   Coordinates Campus Student Ambassador Program.  Site chair of the NCTC Career Fair.  Co-chair of the NCTC-TRF Career Exploration Days Committee.   Coordinates the college wide-system for capturing, coding and qualifying inquiries (ISRS).  Oversees prospect communication letter flow.


Advisor/Recruiter (EGF) – Recruiter duties include conducting high school visits, tours, career fairs, career exploration events, open houses, and orientations.  Coordinates Campus Student Ambassador Program.  Responsible for assisting the Equity Coordinator with nontraditional recruiting efforts.  Prospect data entry.
Student Services Receptionist (TRF) – Duties include main receptionist for the student service department.  Coordinate campus tours.  Prospect data entry.  Responsible for weekly college prospect communications.   Supervise student service work study students.  Serve as backup for Admissions. 

Student Services Receptionist (EGF) – Duties include main receptionist for the student service department.  Prospect data entry.   Serve as backup for Admissions.
Admission Clerk (TRF) – Position exists to process applications, collect application fee, acquire and record high school transcripts or equivalent, acquire and record college transcripts, and process transcript requests. Responsible for campus admission communications.   

Admission Clerk (EGF) – Position exists to process applications, collect application fee, acquire and record high school transcripts or equivalent.  Schedule Faculty Information Sessions.  Responsible for campus admission communications.   

Responsibility: 


 Dean of Student Services and Director of Enrollment Management.
	


Key Strategy 3: 

Develop a college wide-system for capturing, coding and qualifying inquiries
Action Plan:

Utilize the MnSCU Integrated Student Record System (ISRS). 
Receive training on new Integrated Student Record System, which will allow enrollment management team to enter data on new student prospects. This system will allow staff to utilize mail merge capabilities for pattern day intervals, and enter data from all interest inquiries.

●Set goal of one week turn around on all inquiries.
●Create a communications menu.

	


Key Strategy 4: 

Collaborate with Marketing and PR personnel to revise current and develop new promotional publications to support the recruitment program
Action Plan: 

Provide input in the development and revision of college materials which include:  college catalog, view book, student academic planner and handbook, high school visit poster, and academic wall calendar. 
Promote and host special events on campus to maximize the number of student contacts.

	Campus Tours
	Honor Band and Choir
	Athletic Events
	Regional Counselors Meetings
	Cultural Activities

	Demo Days
	Aviation Open House
	HS Tourneys
	Young Authors 
	Career Exploration
Days


Responsibility: 

Enrollment Management, Marketing and Public Relations Departments, as well as Athletic Department.
Timeline: 
On Going 
Cost:



Catalog, View book and Handbook (Marketing Budget)


High School Posters and Calendar (Admissions’ Budget ) 
	


Key Strategy 5:

Develop an effective Student Ambassador Program that includes the use of current students
Action Plan: 
Utilize campus ambassadors during recruiting process. Allow students to act as campus ambassadors and liaisons for all students. Implement a student ambassador-training program that includes campus tours, mentorship’s, and orientations.

Responsibility:

Advisor/Recruiter  (TRF) and Advisor/Recruiter (EGF).

Cost:

$1,000 for each campus
Timeline:

Ongoing.

	


Key Strategy 6:

Develop an enrollment plan for students in targeted segments. Increase enrollment of minority , underrepresented, nontraditional students including nontraditional by gender and program major.
Action Plan: 

· Develop a recruiting guide and calendar for the recruitment of minority, underrepresented and nontraditional students.
● 
Develop a recruiting guide and calendar to promote program majors that are nontraditional by gender. Examples of the programs are: Aviation Maintenance, Auto Body, HVAC, Plumbing, and Medical Coding.
· Utilize current ISRS system to analyze data and inquiries to effectively communicate with these targeted populations. 
· Foster on going partnerships with community and regional agencies, Area Learning Centers, Workforce Centers, Reservation Tribal Offices, and Social Service Agencies etc.
· Enhance current cultural celebrations on campuses: Black History Month, Native Images Month, Women’s History Month and Celebramos (Hispanic Heritage Month). 
· Cooperative ventures with area and local high schools and community agencies would/could bring in regional and local performers, speakers and presentations to our community.

High School Visits
(Underrepresented Student Populations)
	Circle of Life 
	Detroit Lakes
	Frazee HS
	Laporte 
	Park Rapids 

	Bagley 
	Walker 
	Bug School
	Cass Lake 
	Bemidji

	Red Lake 
	Kelliher 
	Blackduck 
	Baudette 
	Warroad 

	Fosston 
	Waubun 
	Mahnomen 
	Lincoln 
	Moorhead 

	Grand Forks
	Fargo
	Bottineau
	Bellcourt
	Rolla

	Rock Lake
	St. John
	Devils Lake
	Warwick
	Sheyenne

	Bisbee
	Dunseith
	Minnewauken
	Rollette
	Kelliher


Native American and Minority Career Fairs

	Red Lake
	Fosston
	Leech Lake
	Detroit Lakes
	White Earth


South Dakota Career Fairs

	Aberdeen
	Sisseton
	Watertown
	Mibank

	Mobridge
	Lemmon
	
	


Alternative Learning Centers
	Thief River Falls
	Grand Rapids
	Grand Forks, ND
	Crookston

	Cass Lake
	Bemidji
	Detroit Lakes
	Grafton


Minnesota Association of Counselors of Color  Career Fairs

	Minneapolis
	St. Paul 
	Metro Area
	
	


National College Fairs

	Minneapolis
	Chicago
	Milwaukee


Responsibility: 

Director of Multicultural Services.

Cost: 
$3,500
Timeline:

Ongoing with major emphasis to start Fall 2007.

	


Key Strategy 7:
Develop a means of sharing recruitment information with members of the faculty, staff and administration
Action Plan:
· Utilize Pioneer Weekly to update NCTC personnel on recruiting schedules on a weekly basis.

· Conduct Recruitment/Enrollment updates at Employee Updates

· Inform personnel of recruitment/enrollment activities during Faculty and Support Staff in-service.
Responsibility:
Director of Enrollment Management. 
Cost:

N.A.

Timeline:

Ongoing.

	


Key Strategy 8:

To continuously improve the college’s ability to communicate with prospective students
Action Plan: 

· Enrollment Management Team will respond within a week to all telephone, internet, walk-in and high school inquiries.

· Enrollment Management Team will prioritize and enter raw data on all new prospects. Incorporate data into ISRS System which will open a communications pattern. 
· Update NCTC web page with the guidance of the College Web Master.

Responsibility:

Enrollment Management Team.

Cost:

N.A.

Timeline:

On-going.

	


[image: image1.jpg]=>>

—NORTHLAND

I::CIMMLINITY

& TECHNICAL
C 0O L L E s E





Enrollment Management Plan

2005-2006
DRAFT
	Programs


EGF # 

TRF# 

Total Enrollment

	

	Accounting


______________________________________

	

	Accounting Clerk

______________________________________

	

	▪Microcomputer

______________________________________

	

	
Administrative Assistant
______________________________________

	

	Administrative Support
______________________________________

	

	▪Bookkeeping

______________________________________

	

	▪Microcomputer

______________________________________

	

	Software Specialist

______________________________________


	Architectural Technology
______________________________________

	

	Auto Body Collision Technology___________________________________

	

	Automotive Service Technology____________________________________

	

	Aviation Maintenance Technology__________________________________

	

	Business


______________________________________

	

	Cardiovascular Technology
______________________________________

	

	Carpentry


______________________________________

	

	Clinical Laboratory Technology____________________________________

	

	Cisco Networking

______________________________________

	

	Computer Modeling and Animation_________________________________

	

	Computer Service/Networking_____________________________________

	Construction Electricity
______________________________________

	

	Cosmetology


______________________________________

	

	▪Esthetist


______________________________________

	

	▪Manicurist


______________________________________

	

	Criminal Justice

______________________________________

	

	Early Childhood & Paraprofessional_________________________________

	

	Farm Operations & Management____________________________________

	

	Health & Fitness Specialist _________________________________________

	

	Health Information Technology_____________________________________

	

	Heating, Ventilation & Air Conditioning______________________________

	

	Individualized Occupational Preparation______________________________

	

	Industrial Mechanical Maintenance__________________________________

	

	Liberal Arts


______________________________________

	

	Manufacturing Process Technology__________________________________

	

	▪ Electronics Emphasis
______________________________________

	

	▪ Welding Emphasis

______________________________________

	

	Marketing


_______________________________________

	

	Mass Communications
_______________________________________

	

	Medical Assisting

_______________________________________

	

	Medical Administrative Secretary____________________________________

	

	Medical Coding & Insurance
_______________________________________

	

	Medical Transcription

_______________________________________

	

	Occupational Therapy Assistant______________________________________

	

	Para medicine


_______________________________________

	

	Pharmacy Technology
_______________________________________

	

	Plumbing Technology

_______________________________________

	

	Practical Nursing

_______________________________________

	

	Registered Nursing

_______________________________________

	

	Radiology Technology
_______________________________________

	

	Respiratory Therapist

_______________________________________

	

	Sales, Marketing, Management______________________________________

	

	Supervisory Leadership
_______________________________________

	

	Surgical Technology

_______________________________________

	

	Truck Driving


_______________________________________

	

	Welding


_______________________________________

	

	

	 

	


PAGE  
5

