## Fairs & Events
Status | Event Date(s) | Event Name | Description | Event Type | Event Category | Location | Target Audience | Notes | Event Director | Event Project Manager (PM) | Event Support Staff | Internal Departments Involved | External Collaborators & Partners
Confirmed | Sept 15, 2025 | MN Education Fair (MACAC) |  | College Fair | Medium Scale Moderate Impact | Thief River Falls, MN Main Campus | HS Students (Grades 10th–12th) | 8/21: Chad sent an email to the college community to raise awareness about the event. 8/26: A news release was published and distributed to media partners and internal audiences. 8/27: A targeted social media ad campaign launched, aligned with K–12 communications. - Comm #1: Sent on 8/28 - Comm #2: Sent on 9/3 | Chad Sperling | Tracy Jo Peterson | Amanda Hoglo Lisa Gunderson | Recruiting Marketing | MACAC
Confirmed | Oct 6–8, 2025 | National College Fair (NACAC) |  | College Fair | Large Scale High Impact | Minneapolis, MN | HS Students (Grades 10th–12th) Parents |  | Chad Sperling | Alyssa Montgomery Amanda Hoglo | Tracy Jo Peterson | Recruiting | Minn State NACAC
Confirmed | 2025-10-11 | Scouting America Badging |  | TBD | Small Scale Targeted Impact | Thief River Falls, MN Aerospace Site | Students (Grades 7th–12th) | Next Steps: Chad is developing a Northland-branded badge design for the medals to be distributed to attending students. Due: 9/4 | Megan Hall | Megan Hall | Chad Sperling Howard Brockhouse | NCAT Marketing Recruiting | Scouting America
Proposed | TBD (Fall) | Grand Forks Schools Building Trades Day (title?) |  | TBD | Small Scale Targeted Impact | East Grand Forks, MN Main Campus | TBD | 9/2 – Event Inquiry from Rick Simon Rick Simon approached Alyssa regarding a potential event. This event was originally organized prior to Chad and Alyssa assuming their current roles, so additional details and historical context are needed to fully understand its background and purpose. Proposed Dates: Monday, October 14 Wednesday, October 16 Time: 9:30 AM – 2:00 PM Requirements: Northland would be responsible for covering event costs and providing lunch. Next Steps: Alyssa to follow up with Rick and Paul Strande to gather historical information, expected audience, and event background. Confirm budget availability for lunch and identify the funding source. | Chad Sperling | Alyssa Montgomery | Tracy Jo Peterson | Recruiting Faculty
Confirmed | 2025-10-22 | Northern Valley Career Expo |  | Career Expo | Large Scale High Impact | Grand Forks, ND | HS Students (Grade 10th) | Northland is confirmed as the marquee sponsor for the event. Booth Space: Need to confirm whether Northland is limited to 10 total booth spaces this year. Confirmed – Northland has unlimited booth space as part of its marquee sponsorship. DroneZone Sponsorship: As of August 15, Northland and NCAT are confirmed as primary sponsors of the new DroneZone feature. Howard Brockhouse will lead coordination and management of this space, in collaboration with Chad Sperling on branding and deliverables. Next Steps: Chad will develop an online registration system that serves as a centralized hub for signing up for multiple events. A comms plan will be created to distribute internal reminders on a scheduled cadence. Registration data will be tracked and reported to the team to support event planning, coordination, and collaboration with event partners. | Chad Sperling Howard Brockhouse (DroneZone) | Alyssa Montgomery Amanda Hoglo | Heather Koland Tracy Jo Peterson | Marketing Recruiting NCAT Admissions Faculty | Becca Kruger (GF EDC)
Proposed | 2025-10-29 | NEW! Minot Area Career Expo |  | Career Expo | Large Scale High Impact | Minot, ND | Students (Grade 9th-10th) | Next Steps: Chad will coordinate with Justin Berry to confirm whether contact has already been made with the Minot organizers and if a booth space has been secured. If not, Chad will explore the possibility of reserving multiple booth spaces to represent Northland more broadly and invite participation from all program faculty. To avoid duplicating efforts or causing confusion, Chad will ensure alignment with any existing plans. 8/18 - Chad submitted inquiry request asking for more info. Justin confirmed he had not reached out to expo reps yet. Next Steps: Chad will develop an online registration system that serves as a centralized hub for signing up for multiple events. A comms plan will be created to distribute internal reminders on a scheduled cadence. Registration data will be tracked and reported to the team to support event planning, coordination, and collaboration with event partners. | Chad Sperling |  | Heather Koland Justin Berry Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
Tentative | 2025-10-31 | NEW! MN HOSA | Minnesota HOSA hosts a statewide career fair focused on health professions, providing a targeted opportunity to engage with high school students interested in healthcare careers. | Conference | Medium Scale Moderate Impact | St. Paul, MN | Students (Grades 6th-College) | Recommendation: Consider securing a booth space and inviting a faculty member from a health-related program to attend alongside a college recruiter to represent the institution and discuss academic pathways in health sciences. | Chad Sperling |  | Heather Koland Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
Proposed | TBD (Fall) | Northland EXPO + Community Open House (Warroad) |  | Career Expo | Large Scale High Impact | Warroad, MN ARC | HS Students (Grades 10th–12th) Community Members | Recommendation: Schedule the Warroad EXPO event in the fall to avoid the logistical challenges of coordinating multiple large-scale events back-to-back. A fall date also minimizes the risk of winter-related cancellations and offers more favorable weather conditions. Additionally, it allows for stronger engagement with area schools, employers, and Northland programs by avoiding overlap with the two main campus EXPOs. Next Steps: Coordinate with ARC (Kim H) and Warroad partners to confirm a fall date that maximizes attendance. Survey faculty to assess interest and identify the most suitable or preferred timeframes for the event. | Chad Sperling |  | Amanda Hoglo Alyssa Montgomery Tracy Jo Peterson Maura Nelson | Marketing Recruiting Admissions Faculty
Confirmed | Nov 6–7, 2025 | T4 Summit | The T4 Summit manages and operates the event, while Northland serves as the host site, coordinating program attendance and hospitality. | Career Expo | Large Scale High Impact | East Grand Forks, MN Main Campus | Middle School Students (Grade 8th) | Next Steps: Chad will develop an online registration system that serves as a centralized hub for signing up for multiple events. A comms plan will be created to distribute internal reminders on a scheduled cadence. Registration data will be tracked and reported to the team to support event planning, coordination, and collaboration with event partners. | Chad Sperling | John Fields Alyssa Montgomery Maura Nelson | Heather Koland Amanda Hoglo Tracy Jo Peterson | Marketing Recruiting Admissions Faculty | Shawn Brink (T4 Summit)
Confirmed | 2025-11-12 | NEW! Region 1 FFA Contests |  | Contest | Small Scale Targeted Impact | Thief River Falls, MN Main Campus | TBD |  | ADawn Nelson |  | Amanda Hoglo Alyssa Montgomery Tracy Jo Peterson | Recruiting Faculty | AgCentric
Confirmed | 2025-11-20 | Experience Aerospace |  | Career Expo | Large Scale High Impact | Thief River Falls, MN Aerospace Site | Students (Grades 7th–12th) |  | Megan Hall |  | Chad Sperling Howard Brockhouse | NCAT Marketing Recruiting Admissions Faculty
Confirmed | Feb 11-12, 2026 | Health Career Fair | Health Division Career Fair exclusively for Northland students. Explore career opportunities, connect with industry professionals, and learn more about your future in healthcare. | Career Fair | Small Scale Targeted Impact | East Grand Forks, MN Main Campus | Current Northland Students |  | Deb Beland | Deb Beland | Alyssa Montgomery Tracy Jo Peterson | Marketing Recruiting Admissions Faculty | TBD
Proposed | TBD (Spring) | T4-like Event (Working Title) |  | Career Expo | Large Scale High Impact | Thief River Falls, MN Main Campus | TBD | Funding/Support: Sponsored by Pine to Prairie Cooperative – $25,000 secured. Next Steps: Chad to schedule a meeting with Tom Leuthner to discuss partnership details, event involvement, and brainstorm naming/branding ideas for the event. Chad emailed Tom to arrange a meeting on 8/15. | Chad Sperling | Amanda Hoglo | Maura Nelson Joseph Agbeko | Marketing Recruiting Admissions Faculty | Tom Leuthner (Pine to Prairie Co-op)
Proposed | TBD (Spring) | Northland EXPO (EGF) |  | Career Expo | Large Scale High Impact | East Grand Forks, MN Main Campus | HS Students (Grades 10th–12th) | Recommendation: The recruiting team recommends holding the event in February to get ahead of the busy spring recruiting season and associated career fairs. This timing would allow for earlier engagement with prospective students and reduce scheduling conflicts later in the semester. Next Steps: Survey faculty to determine the most suitable or preferred time frames for the event. 8/20-21: Survey shared with all faculty at inservice and in a follow up email. | Chad Sperling |  | Amanda Hoglo Alyssa Montgomery Tracy Jo Peterson Maura Nelson | Marketing Recruiting Admissions Faculty
Proposed | TBD (Spring) | Northland EXPO (TRF + Aero) |  | Career Expo | Large Scale High Impact | Thief River Falls, MN Main Campus Aerospace Site | HS Students (Grades 10th–12th) | Same recommendation and next steps as EGF EXPO. | Chad Sperling |  | Amanda Hoglo Alyssa Montgomery Tracy Jo Peterson Maura Nelson | Marketing Recruiting Admissions Faculty NCAT
Confirmed | 2026-03-09 | Behind The Mask | The "Behind the Mask" event is an American Welding Society (AWS) welding competition held annually for high school and college students. It provides a platform for students to showcase their welding skills, network with industry professionals, and potentially win prizes. | Contest | Small Scale Targeted Impact | Thief River Falls, MN Main Campus | TBD | 8/21: Chad emailed Joel asking for details on this event. Joel confirmed date and location of event. More details to come. | Joel Zeigler |  | Amanda Hoglo Alyssa Montgomery Tracy Jo Peterson | Recruiting Faculty | American Welding Society
Tentative | March 9-11, 2026 | NEW! MN HOSA | Minnesota HOSA hosts a statewide career fair focused on health professions, providing a targeted opportunity to engage with high school students interested in healthcare careers. | Conference | Medium Scale Moderate Impact | St. Cloud, MN | Students (Grades 6th-College) | Recommendation: Consider securing a booth space and inviting a faculty member from a health-related program to attend alongside a college recruiter to represent the institution and discuss academic pathways in health sciences. | Chad Sperling |  | Heather Koland Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
Proposed | TBD (Spring) | NEW! Franklin Middle School Career Day | An event opportunity where faculty and/or recruiting staff can engage with students to present career pathways and the educational programs that support them. | Career Day | Small Scale Targeted Impact | Thief River Falls, MN | TBD | Next Steps: Maura Nelson will reach out to schools to gather additional details and assess interest. | Chad Sperling |  | Maura Nelson Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
Tentative | TBD (Spring) | NEW! EGF Middle School(s) Career Day | An event opportunity where faculty and/or recruiting staff can engage with students to present career pathways and the educational programs that support them. | Career Day | Small Scale Targeted Impact | East Grand Forks, MN | TBD | Next Steps: Maura Nelson will reach out to schools to gather additional details and assess interest. | Chad Sperling |  | Maura Nelson Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
Tentative | TBD (Spring) | NEW! Grand Forks Middle School(s) Career Day | An event opportunity where faculty and/or recruiting staff can engage with students to present career pathways and the educational programs that support them. | Career Day | Small Scale Targeted Impact | Grand Forks, ND | TBD | Next Steps: Maura Nelson will reach out to schools to gather additional details and assess interest. | Chad Sperling |  | Maura Nelson Amanda Hoglo Alyssa Montgomery | Recruiting Faculty
KEY
Category | Description
Large Scale High Impact | Regional or statewide events with broad reach, high attendance, and strategic value
Medium Scale Moderate Impact | Local or multi-school events with targeted engagement and moderate visibility
Small Scale Targeted Impact | Niche or specialized events with focused audiences and limited scope